## Group Contribution Log
Course | CS3342 Software Design
Year | 2026
Project No. | 26
Project Name/Title | LastMile
No. of Team Members | 4
Project Manager Name | Lessov Akniyet
Student ID | Name (Last, First) | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Total | Student | Relative | Contribution | e.g.Group Mark | Final Adjusted
| Lessov Akniyet | 2 | 3 | 6 | 4 | 5 | 5 | 4 | 4 | 6 | 4 | 4 | 5 | 3 | 55 | Lessov Akniyet | 1.5827 | 100% | 80 | 80
| Bulatov Smadiyar | 1 | 2 | 3 | 2 | 2 | 3 | 2 | 2 | 3 | 3 | 2 | 3 | 2 | 30 | Bulatov Smadiyar | 0.86331 | 54.55% | 80 | 43.6364
| Naumov Iusuf | 1 | 1 | 3 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 2 | 3 | 2 | 28 | Naumov Iusuf | 0.80576 | 50.91% | 80 | 40.7273
| Tursynov Birzhan | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 26 | Tursynov Birzhan | 0.7482 | 47.27% | 80 | 37.8182
[15 empty] | 0 | 0 | 0 | 0% | 80 | 0
[15 empty] | 0 | 0 | 0 | 0% | 80 | 0
| Total Effort | 5 | 7 | 14 | 10 | 11 | 12 | 11 | 10 | 15 | 11 | 10 | 14 | 9 | 139 | Max | 1.5827 |  | Average | 33.697
[19 empty] | Max | 80
[19 empty] | Min | 0

## Weekly Activity Log
Week | Weekly Activity Log | Completed By
Week 1 | Recruit project members. Form the team and discuss project ideas. | All team members
Week 2 | Information collection. Research delivery route optimization algorithms and existing solutions. | All team members
Week 3 | Topic selection and feasibility analysis. Chose Java CLI route optimizer with TSP heuristics. | All team members
Week 4 | Define requirements and core functionality. Identify key features: algorithms, constraints, reporting. | All team members
Week 5 | Finalize requirements and use case modeling. Draft use case diagrams for route planning workflow. | All team members
Week 6 | Begin use case descriptions. Set up Maven project structure and core data models (DeliveryGraph, Package, Route). | All team members
Week 7 | Implement Nearest Neighbor and Greedy Edge algorithms. Design class diagrams and sequence diagrams. | All team members
Week 8 | Implement 2-Opt improvement algorithm and Observer pattern (ConsoleLogger, FileLogger, ConstraintChecker). | All team members
Week 9 | Implement Template Method for report generation. Finalize class diagrams and sequence diagrams. | All team members
Week 10 | Apply design patterns (Strategy, Observer, Template Method). Refine diagrams for pattern integration. | All team members
Week 11 | Write JUnit 5 test suite (30+ tests across 8 classes). Begin documentation (README, User Manual). | All team members
Week 12 | Finish prototype, build fat JAR with Maven Shade plugin. Complete Installation Guide and documentation. | All team members
Week 13 | Prepare presentation slides and finalize report. Demo rehearsal and final review. | All team members